## Sheet1
Play 1: | Understand what people need | Comments
| Early in the project, spend time with current and prospective users of the service | Brainstorming session with larger team. We included people from the company who have had greater interest in pharmaceuticals for health purposes.
| Use a range of qualitative and quantitative research methods to determine people’s goals, needs, and behaviors; be thoughtful about the time spent | Collected Quantitative data during the usability tests by measuring time to completion, error rates, clicks to completion. Qualitative data collected in notes and observations.
| Test prototypes of solutions with real people, in the field if possible | Paper Prototype Usability Test performed 6/22
| Document the findings about user goals, needs, behaviors, and preferences | Metrics recorded, Feedback shared and registered as "issues" in github
| Share findings with the team and agency leadership | Issues shared at sprint review which were then converted to new user stories to resolve
| Create a prioritized list of tasks the user is trying to accomplish, also known as "user stories" | User Stories are created, followed, and worked in the Scrum Do project management tool
| As the digital service is being built, regularly test it with potential users to ensure it meets people’s needs | Multiple tests with users beginning with paper prototype, then when working prototype is created, moving into that phase.
Play 2: | Address the whole experience, from start to finish | Comments
| Understand the different points at which people will interact with the service – both online and in person | Competetive Analysis, Paper Prototype Usability Test
| Identify pain points in the current way users interact with the service, and prioritize these according to user needs | Paper Prototype Usability Test, Working Prototype Usability Test
| Design the digital parts of the service so that they are integrated with the offline touch points people use to interact with the service | N/A
| Develop metrics that will measure how well the service is meeting user needs at each step of the service | Future Enhancement
Play 3: | Make it simple and intuitive | Comments
| Create or use an existing, simple, and flexible design style guide for the service | Style Guide created, easily updated
| Use the design style guide consistently for related digital services | No related digital services created as of submission date.
| Give users clear information about where they are in each step of the process | Usability Tests did not reveal a "lost" scenario.
| Follow accessibility best practices to ensure all people can use the service | 508 compliant
| Provide users with a way to exit and return later to complete the process | Future Enhancement -- "Save List"
| Use language that is familiar to the user and easy to understand | Used medical consumer language when identifying data points.
| Use language and design consistently throughout the service, including online and offline touch points | Language is consistent.
Play 4: | Build the service using agile and iterative practices | Comments
| Ship a functioning “minimum viable product” (MVP) that solves a core user need as soon as possible, no longer than three months from the beginning of the project, using a “beta” or “test” period if needed | Working prototype on 2nd day
| Run usability tests frequently to see how well the service works and identify improvements that should be made | Executed paper prototype and functional prototype usability tests
| Ensure the individuals building the service communicate closely using techniques such as launch meetings, war rooms, daily standups, and team chat tools | Kickoff meeting, daily standup, working conference room, and Skype are all tools used by the team.
| Keep delivery teams small and focused; limit organizational layers that separate these teams from the business owners | Team has direct access to product owner
| Release features and improvements multiple times each month | 3 sprint releases in the span of 1 week.
| Create a prioritized list of features and bugs, also known as the “feature backlog” and “bug backlog” | Backlog is continuously groomed in Scrum Do. It features sprint backlog, defect backlog, and product backlog.
| Use a source code version control system | GitHub
| Give the entire project team access to the issue tracker and version control system | GitHub
| Use code reviews to ensure quality | GitHub --> docs/scrum/sprint*
Play 5: | Structure budgets and contracts to support delivery | Comments
| Budget includes research, discovery, and prototyping activities | Team used first weekend to research and prototype. Vance was retained to perform that prototype.
| Contract is structured to request frequent deliverables, not multi-month milestones | No contract, but sprints were divided into 2 day periods
| Contract is structured to hold vendors accountable to deliverables | No contract
| Contract gives the government delivery team enough flexibility to adjust feature prioritization and delivery schedule as the project evolves | No contract
| Contract ensures open source solutions are evaluated when technology choices are made | No contract
| Contract specifies that software and data generated by third parties remains under our control, and can be reused and released to the public as appropriate and in accordance with the law | No contract
| Contract allows us to use tools, services, and hosting from vendors with a variety of pricing models, including fixed fees and variable models like “pay-for-what-you-use” services | No contract
| Contract specifies a warranty period where defects uncovered by the public are addressed by the vendor at no additional cost to the government | No contract
| Contract includes a transition of services period and transition-out plan | No contract
Play 6: | Assign one leader and hold that person accountable | Comments
| A product owner has been identified | Keith Alphonso is product owner. He remains active and engaged.
| All stakeholders agree that the product owner has the authority to assign tasks and make decisions about features and technical implementation details | Keith is granted authority over the use of resources and is solely responsible for the quality of this product.
| The product owner has a product management background with technical experience to assess alternatives and weigh tradeoffs | Keith is CTO of Geocent.
| The product owner has a work plan that includes budget estimates and identifies funding sources | PMP, Attachment C is our budget, funding is internal, approved by ORB process
| The product owner has a strong relationship with the contracting officer | N/A
Play 7: | Bring in experienced teams | Comments
| Member(s) of the team have experience building popular, high-traffic digital services | Tyler Sanders for DevOPs Lead
| Member(s) of the team have experience designing mobile and web applications | Aaron and Josh lead this effort
| Member(s) of the team have experience using automated testing frameworks | Tyler and Josh lead this effort to train team on Protractor
| Member(s) of the team have experience with modern development and operations (DevOps) techniques like continuous integration and continuous deployment | Tyler Sanders for DevOPs Lead: using AWS, docker, jenkins
| Member(s) of the team have experience securing digital services | N/A
| A Federal contracting officer is on the internal team if a third party will be used for development work | N/A
| A Federal budget officer is on the internal team or is a partner | N/A
| The appropriate privacy, civil liberties, and/or legal advisor for the department or agency is a partner | N/A
Play 8: | Choose a modern technology stack | Comments
| Choose software frameworks that are commonly used by private-sector companies creating similar services | AngularJS JS/UI Framework MIT Docker Production Deployment Contain for isolation Apache Bootstrap Responsive UI MIT Gulp Automated Build/Workflow MIT Protractor E2E Testing MIT NVM Node Versioning Manager for local Devleopment Environment MIT D3 JS Used for charts and data driven documents AS IS NVD3 Reusable charts component for D3 Apache Style-Guide-Boilerplate-Bootstrap-Edition Generate Style Guide MIT
| Whenever possible, ensure that software can be deployed on a variety of commodity hardware types | Utilizing Docker for container so we are only limited to hardware/OS that can support Docker
| Ensure that each project has clear, understandable instructions for setting up a local development environment, and that team members can be quickly added or removed from projects | Readme-dev is on github and has been tested by other devs as successful as they come into the project. Any discrepancies are addressed by updating the readme if applicable.
| Consider open source software solutions at every layer of the stack | Fully open source
Play 9: | Deploy in a flexible hosting environment | Comments
| Resources are provisioned on demand | AWS
| Resources scale based on real-time user demand | Future enhancement
| Resources are provisioned through an API | AWS
| Resources are available in multiple regions | AWS
| We only pay for resources we use | AWS
| Static assets are served through a content delivery network | Future enhancement
| Application is hosted on commodity hardware | AWS
Play 10: | Automate testing and deployments | Comments
| Create automated tests that verify all user-facing functionality | Protractor is used for E2E testing against the browser.
| Create unit and integration tests to verify modules and components | Karma used for unit tests / Protracter used for integration tests
| Run tests automatically as part of the build process | Docker and Gulp
| Perform deployments automatically with deployment scripts, continuous delivery services, or similar techniques | Jenkins auto deploys 'integration' (dev) builds to 'ads-dev' while 'master' is deployed to 'asd.geocent.com'
| Conduct load and performance tests at regular intervals, including before public launch | Future enhancement
Play 11: | Manage security and privacy through reusable processes | Comments
| Contact the appropriate privacy or legal officer of the department or agency to determine whether a System of Records Notice (SORN), Privacy Impact Assessment, or other review should be conducted | OpenSource Software. License on GitHub
| Determine, in consultation with a records officer, what data is collected and why, how it is used or shared, how it is stored and secured, and how long it is kept | No data is collected from site inputs
| Determine, in consultation with a privacy specialist, whether and how users are notified about how personal information is collected and used, including whether a privacy policy is needed and where it should appear, and how users will be notified in the event of a security breach | No personal info is collected or stored
| Consider whether the user should be able to access, delete, or remove their information from the service | No personal info is collected or stored
| “Pre-certify” the hosting infrastructure used for the project using FedRAMP | N/A
| Use deployment scripts to ensure configuration of production environment remains consistent and controllable | Deployment scripts used in CI. Will need to build out for production.
Play 12: | Use data to drive decisions | Comments
Monitor system-level resource utilization in real time
Monitor system performance in real-time (e.g. response time, latency, throughput, and error rates)
Ensure monitoring can measure median, 95th percentile, and 98th percentile performance
Create automated alerts based on this monitoring
Track concurrent users in real-time, and monitor user behaviors in the aggregate to determine how well the service meets user needs
Publish metrics internally
Publish metrics externally
Use an experimentation tool that supports multivariate testing in production
Play 13: | Default to open | Comments
| Offer users a mechanism to report bugs and issues, and be responsive to these reports | Once Github is open, link this to ask users to report through the issues tracker
| Provide datasets to the public, in their entirety, through bulk downloads and APIs (application programming interfaces) | This app uses the OpenFDA dataset. Refer to that should get a win here
| Ensure that data from the service is explicitly in the public domain, and that rights are waived globally via an international public domain dedication, such as the “Creative Commons Zero” waiver | Data is from OpenFDA, limited to FDA ToS.
| Catalog data in the agency’s enterprise data inventory and add any public datasets to the agency’s public data listing | Data is from OpenFDA, limited to FDA ToS.
| Ensure that we maintain the rights to all data developed by third parties in a manner that is releasable and reusable at no cost to the public | Government owns the source data. OpenFDA.
| Ensure that we maintain contractual rights to all custom software developed by third parties in a manner that is publishable and reusable at no cost | N/A
When appropriate, create an API for third parties and internal users to interact with the service directly
| When appropriate, publish source code of projects or components online | Published via GitHub. This GitHub project is open.
| When appropriate, share your development process and progress publicly | Will be shared as a response to this RFP.