## Slide 1: NOTICE: Proprietary and Confidential This material is proprietary to Geocent. It contains trade secrets and confidential information which is solely the property of Geocent. This material is solely for the Client’s internal use. This material shall not be used, reproduced, copied, disclosed, transmitted, in whole or in part, without the express consent of Geocent. © 2009 All rights reserved
Centered on Solutions
GSA 18F BPA Agile RFQ
Sprint: Stabilization Planning
June 29, 2015
Sprint Artifact

## Slide 2
Goals/Dependencies/Definition of Done
Discussion Points/Stories
Sprint Schedule
Agenda

## Slide 3
Sprint: Stabilization
Goals:
  Clean up issues (GitHub), finish stories (ScrumDo), and stabilize application
Dependency:
  None
Definition of Done:
  Issues completed in GitHub
  Pass testing in Integration branch/CI
  Validated Unit Tests
  Validated End-to-End Tests
  Validated User Acceptance Testing
  Validated Usability Testing

## Slide 4
Sprint: Stabilization
How do we want to do this?
  Issue Tracker??? Put issues in ScrumDo???
    Could prioritize by label within the name High, Med, Low
    DECISION: Issues will be worked and tracked in GitHub – must indicate in comment section that you are working and status – currently 11 issues – 2 are top priority
Finish up on the little things
IE 11 Issue
  Policy in client
  Group Policy setting in IE that is part of Security settings
  Issue with IE 11 stems from Compatibility Mode setting
Current version has reduced number of queries, has eliminated issues
#40 Need better error handling – No Data Found – Too Many Queries, condition set by DB – says you have exceeded the data limits of the OpenFDA – state to try again , white out screen. (Story #40)
Results coming out inconsistent, check aggregation for the fields (Aaron)
Button to generate Demographics chart – wouldn’t run each time – concern if user repeatedly clicks button will overload the queries
#41 better handling when no drugs are returned, hide all charts
Issue: How to get this to work text needs to go above boxes, needs to move for mobile device (Josh)
Issue: 508 compliant – Aaron working list – needs clarification – Alt on Chart information not clear where elements in app violates it, anticipate tedious, time consuming, unsure of definition of done, most are addressed – don’t know what actually violates (keith will contact Vance)

## Slide 5
Sprint: Stabilization (continued)
Top Priority: Error handling
Change prescription to drugs (Jared)
Report date as a column (low)
Symptoms that are not common to non-medical personnel – possible add a link that opens WebMD to get a description from graph – done on the table, explore the details (Medium)
Keith will set priority HIGH to Issues that need to be completed
Finish final stories in ScrumDo
Each person needs to sign up for issues for workflow purposes
What needs to be done to move to Production?
Screen shots of cloud watch working on the host (Tyler)
Test Coverage (Josh)
Plan
1. Finish Stories in ScrumDo
2. Prioritization of Issues in GitHub
Work Issues High, Medium, Low
Review: 2:00 tomorrow 6/30

## Slide 6
Sprint Schedule
Sprint 0 – Capture Sprint
  6/17/2015
  Sprint 0 Planning: 6/17
  Sprint 0 Review: 6/18
Sprint 1 – Architecture, Development, Testing
  6/18/2015 – 6/22/2015
  Sprint 1 Planning: 6/18
  Sprint 1 Review: 6/23
Sprint 2 – Finalize Product, Final QA Testing, User Testing
  6/23/2015 – 6/24/2015
  Sprint 2 Planning: 6/23
  Sprint 2 Review: 6/25
Sprint 3 – Usability Enhancement
  6/25/2015 – 6/29/2015
  Sprint 2 Planning: 6/25
  Sprint 2 Review: 6/29
Sprint Stabilization
  6/30/2015
Deliver
  7/1/2015
Completed
Completed
Completed
Completed

## Slide 7
Questions