## Slide 1: NOTICE: Proprietary and Confidential This material is proprietary to Geocent. It contains trade secrets and confidential information which is solely the property of Geocent. This material is solely for the Client’s internal use. This material shall not be used, reproduced, copied, disclosed, transmitted, in whole or in part, without the express consent of Geocent. © 2009 All rights reserved
Centered on Solutions
GSA 18F BPA Agile RFQ
Sprint 1 Planning
June 18, 2015
Sprint Artifact

## Slide 2
Goals/Dependencies/Definition of Done
Sprint Schedule
Artifacts Needed
Discussion Points
Branching Strategy
Sprint Schedule
Sprint 1 Schedule
Agenda

## Slide 3
Sprint 1: Architecture, Development, and Test
Goals:
  Finalize Architecture
  Begin Development
  Establish Testing Plan and implement
  Basic capabilities to initiate the search (query to pull data) and display of results (graphics, lists, 3D models)
  Focus on Product and Process
Dependency:
  UI wireframe needs to be completed – target by COB 6/18
Definition of Done: Sprint 1
  Development Stories
  Tested in Integration branch/CI
  Unit Test validation (Jenkins),
  End-to-End validation (Jenkins)

## Slide 4
Sprint 1
Artifacts Needed:
  Features from Vision Document created into Stories, determined only 1 story is needed to capture all items that will be searched and results returned
    Stories 23, 24, 25, and 26 moved to one story #23
  Need a license/tool/technologies chart – Angular, Protractor, Jenkins, JUnit, Jazz Syntax
  Set up CI and CM – Keith/Jared
  CI Design doc
  CM doc
  PMP and QA need finalization – Jared/Brian
  Org chart for project
  Playbook – record details of work in google docs and extract text from Skype to document project progress
  Defects/Issue Management Process documents
  Domains needed with SSL searches

## Slide 5
Sprint 1
Discussion Points:
  Drug Interaction Report Finder (need name for the app)
  Account Query
  Determine exact match
  List of drugs returned from the search – how to display the list
  Identify and consider other conditions that affect the drug interactions – sex, age, race, etc
  Way to search with or without full name of drug
  Identify source control for Configuration Management - GitHub
  Does app need to capture user’s username and password (no)
  Need Use cases, CI and Continuous monitoring details
  CI – monitoring deployment of software – automated deployment to prod
  Dev environment set – auto deploy to master, deploy to CI, prod auto deployment, tag release to Jenkins
  Enforce Story ID expression at the beginning of the branch using brackets [ ]

## Slide 6
Sprint 1: Capture Sprint
Discussion Points (continued):
  CI design – Tyler – up and running will document
    CI environment and Prod – duel staging
    Track by branch – release tag
    Release pushes the tag
  Continuous Monitoring (CM) identify what criteria will go into the release
    Bootstrap – responsive design – consider
    Mobile App – HTM5
    Develop desktop version first then look at mobile app
  1 master branch across stories – 1 branch per story

## Slide 7
Sprint 1: Branching Strategy
Pull from Integration branch making sure it is fully tested to keep master branch stable
CI monitors integration and prod
Establish a User Testing Team – create forms, metrics – target review of UI 06/20

## Slide 8
Sprint Schedule
Sprint 0 – Capture Sprint
  6/17/2015
  Sprint 0 Planning: 6/17
  Sprint 0 Review: 6/18
Sprint 1 – Architecture, Development, Testing
  6/18/2015 – 6/22/2015
  Sprint 1 Planning: 6/18
  Sprint 1 Review: 6/23
Sprint 2 – Finalize Product, Final QA Testing, User Testing
  6/23/2015 – 6/24/2015
  Sprint 2 Planning: 6/23
  Sprint 2 Review: 6/25
Sprint 3 – Stabilization Sprint
  6/25/2015
Deliver
  6/26/2015
Completed

## Slide 9
Sprint 1: Schedule

## Slide 10
Questions