## Slide 1: NOTICE: Proprietary and Confidential This material is proprietary to Geocent. It contains trade secrets and confidential information which is solely the property of Geocent. This material is solely for the Client’s internal use. This material shall not be used, reproduced, copied, disclosed, transmitted, in whole or in part, without the express consent of Geocent. © 2009 All rights reserved
Centered on Solutions
GSA 18F BPA Agile RFQ
Drug IQ
Sprint 2 Review
June 25, 2015
Sprint Artifact

## Slide 2
Goals/Definition of Done
Artifacts: Status
Technologies Chart
Organizational Chart
Architectural Diagrams
Mock Up Issue
Playbook Checklist
Sprint 2 Demonstration
Sprint 2 Stories
Sprint 2 Burndown Chart
Sprint Schedule
Sprint 2 Retrospective
Agenda

## Slide 3
Sprint 2: Prototype Finalization
Goals:
  Finalize Architecture
  Finalize Prototype Development
  Implement Testing Plan and produce report/metrics
  Address changes to Mock up
Dependency:
  None
Definition of Done: Sprint 2
  Prototype completed
  Pass testing in Integration branch/CI
  Validated Unit Tests
  Validated End-to-End Tests
  Validated User Acceptance Testing

## Slide 4
Sprint 2: Artifacts
Read Me
  Update License/Tools/Technologies Chart - Done
    https://github.com/Geocent/18f-prototype/blob/integration/README.md
PMP
  Org Chart for Project - Done
    https://github.com/Geocent/18f-prototype/blob/integration/docs/scrum/sprint2/Geocent%20Project%20Management%20Plan%20-%20Sprint2.docx
  Defect/Issue Management Process - Done
    https://github.com/Geocent/18f-prototype/blob/integration/docs/scrum/sprint2/Geocent%20Project%20Management%20Plan%20-%20Sprint2.docx
  Documentation for CI
    Reference Architecture Diagram and add link to PMP
  Documentation for CM design
    Using GitHub need to add to PMP
  Final QA document – Delivery Management Quality Plan
    Need meeting to discuss content for PMP
    Provide link to Code Review Form

## Slide 5
Sprint 2: Artifacts
Architecture Diagram - In progress
  https://github.com/Geocent/18f-prototype/blob/integration/docs/scrum/sprint2/architecture-diagram_Sprint2.pdf
UI Mock Up
  Need to discuss and document changes made during Prototype development
Playbook Checklist – In progress
Discussion: Change used only Calling drug event – may need to address and redesign to expand events to pull all of the right drugs.

## Slide 6
Sprint 2: UI Mock Up
Discussion:
Minor changes made to UI Mock Up for Prototype to present a better view based on usability testing results, technical issues in terms of the number of records being displayed, choosing symptoms before the displays.
Keith and Vance will look at UI based on usability testing results; will create a story for enhancements and prioritize tasks based on feedback.

## Slide 7
Sprint 2: Playbook Checklist
Discussion:
Well covered and good justifications and not applicable identified
Needs review docs.hcd
Add to readme – playbook link and justifications
https://github.com/Geocent/18f-prototype/tree/integration/docs/HCD

## Slide 8
Sprint 2: Demonstration

## Slide 9
Sprint 2: Stories
Discussion:
Stories
  #31 – look at color scheme when hovering over link
  #10 – runs on multiple devices, mobile driver needs adjustments, create enhancements
  #26 – check box for seriousness works well
  All other stories look good
  #27 – working
Acceptance
  All completed stories accepted
  1 story still in progress
Enhancements
  Click view report – opens – only 1 data field, need additional fields to report
https://www.scrumdo.com/projects/project/18f-ads-prototype/iteration/128771

## Slide 10
Sprint 2: Burndown Chart
https://www.scrumdo.com/projects/project/18f-ads-prototype/iteration/128771

## Slide 11
Sprint Schedule
Sprint 0 – Capture Sprint
  6/17/2015
  Sprint 0 Planning: 6/17
  Sprint 0 Review: 6/18
Sprint 1 – Architecture, Development, Testing
  6/18/2015 – 6/22/2015
  Sprint 1 Planning: 6/18
  Sprint 1 Review: 6/23
Sprint 2 – Finalize Product, Final QA Testing, User Testing
  6/23/2015 – 6/24/2015
  Sprint 2 Planning: 6/23
  Sprint 2 Review: 6/25
Sprint 3 – Enhancement
  6/25/2015 – 6/29/2015
  Sprint 2 Planning: 6/25
  Sprint 2 Review: 6/29
Sprint 3 – Stabilization Sprint
  6/29/2015
Deliver
  7/1/2015
Completed
Completed
Completed

## Slide 12
Sprint 2: Retrospective
What went well?
  Instant feedback on CI ADS-Dev – was great, as soon as commit, was available to look at, way it should be
  Infrastructure was awesome
  Adapted to issues rapidly – made UI, functional issues – pretty responsive
  Chat ability went steady all day allowing for rapid reactive changes
  Emails from broken builds – immediately know something went wrong – generated from Jenkins CI
  User Acceptance Testing issues/bugs/changes into GitHub allowed for instant feedback and changes could be made
  High success patch rate
What did not go well?
  Skype for business is a challenge for meetings
  Merge into integration steady stream of check-in into integration – challenge ready to check-in but someone made changes, had to take a step back (find happy medium to mitigate the challenge), may need more servers, Jenkins job or add process to slow down features into CI – solution: need to pull down updates before commit
  Code review process needed, should be id in project kick-off – code related stories, add task for code review, we did have it as definition of done
What would you change?
  CI for every feature branch (Ok on large project, not sure of feasibility for smaller projects)
  Need a check-in the code review form earlier in process

## Slide 13
Questions