## Slide 1: NOTICE: Proprietary and Confidential This material is proprietary to Geocent. It contains trade secrets and confidential information which is solely the property of Geocent. This material is solely for the Client’s internal use. This material shall not be used, reproduced, copied, disclosed, transmitted, in whole or in part, without the express consent of Geocent. © 2009 All rights reserved
Centered on Solutions
GSA 18F BPA Agile RFQ
Sprint 0 Review
June 18, 2015
Sprint Artifact

## Slide 2
Sprint 0 Goal
Accomplishments
Action Items
Process for Acceptance
Definition of Done
List of Technologies
Architectural Diagram
Sprint 0 Stories
Sprint 0 Burndown Chart
Sprint Schedule
Agenda

## Slide 3
Sprint 0: Capture Sprint
Goals:
  Create Vision Document
  Identify Epics, Stories
  Establish Infrastructure
  Choose Technical Approach
  Create Architectural Diagram
    set up virtual architecture design meeting
  Create Table of Technologies
    list benefit for each and how they will be used
  Establish Testing Plan
    identify technology for code testing, identify user testing pool
  Identify Name of Product
  Create CI/CM document

## Slide 4
Sprint 0: Capture Sprint
Accomplishments:
  Reviewed Architecture diagram, discussed adjustments
  Discussed Technologies for CI
  Ensure security through branch strategy, after code review and before check in to master
  PMP and QA process documented, in final review – Jared
Action Item:
  Need to apply for API keys

## Slide 5
Sprint 0: Capture Sprint
Process for Acceptance
  Angular, Protractor for Unit Test, End-to-End Test, and Jazz Syntax
  Jenkins for Unit Test and CI build, Integration Test (End-to-End) once deployed
  Unit Test completed by Dev
  Check in to branch
  Pull request (QA) review – check in to approve
  Before close out merge into master
  Protractor Test
  Wrap Jenkins with job if fails, output to Junit to determine results (Gult)
  Automatic check in to branch – look at master and pull request to review before goes into master
  Set Jenkins feature branch into pipeline for Integration Test
Definition of Done
  Unit Test on Dev level
  Unit Test Jenkins
  CI Build
  Integration Test
  Merge to Master

## Slide 6
Sprint 0: Technologies

## Slide 7
Sprint 0: Architectural Diagram

## Slide 8
Sprint 0: Stories

## Slide 9
Sprint 0: Burndown Chart

## Slide 10
Sprint Schedule
Sprint 0 – Capture Sprint
  6/17/2015
  Sprint 0 Planning: 6/17
  Sprint 0 Review: 6/18
Sprint 1 – Architecture, Development, Testing
  6/18/2015 – 6/22/2015
  Sprint 1 Planning: 6/18
  Sprint 1 Review: 6/23
Sprint 2 – Finalize Product, Final QA Testing, User Testing
  6/23/2015 – 6/24/2015
  Sprint 2 Planning: 6/23
  Sprint 2 Review: 6/25
Sprint 3 – Stabilization Sprint
  6/25/2015
Deliver
  6/26/2015
Completed

## Slide 11
Questions